## 00 README
TheLastClicks — SEO / AI-search sprint tracker · 8 Sep – 5 Oct 2026
Scope: Reddit & Quora · Blog · Citations & roundups · Baseline. (Reviews and YouTube tracks from the presence-plan PDF are out of scope here.)
Tabs:
01 Sprint calendar — one row per task, dated. Tick Done, paste result URL. ~5.5 h/week.
02 Reddit · subs / threads / log — where to be, which threads exist today, and a contribution log that enforces the 9:1 rule.
03 Quora · questions / rules & template — 25 real questions with follower/answer/view counts; 7 scheduled, rest month-2 backlog.
04 Blog · calendar / rules — four posts fully specified (capsule, H2s, links, evidence, hard rules).
05 Citations · list / NAP master / rules / Roundups & pitches — tiered platform list with URL, cost, verification, category; copy NAP only from the master.
06 Baseline · prompts / engines / AI log / weekly / setup steps — month-zero measurement, pre-filled 84-row AI log, weekly KPI row.
Hours: W1 ≈ 9.75 (one-off 2.5 h baseline + author page + hub refresh) · W2 ≈ 6.5 · W3 ≈ 6.5 · W4 ≈ 8.5 incl. 2 h stretch post. Rows flagged in 'Cut first' bring W1 to ≈ 8.75, W3 to ≈ 6, W4 to ≈ 5.25.
Standing rules (all tracks): never fake anything · one NAP byte-identical everywhere · no ₹ figures and no turnaround promises anywhere public · buyer language, never internal labels · every profile links the site · free tiers only this month.
Companion document: docs/seo/2026-09-sprint-reddit-quora-blog-citations.md (the why behind every row, with sources).

## 01 Sprint calendar
One row per task. Tick Done, paste the live URL. 4-6 h/week total. Tracks: Baseline · Citations · Reddit · Quora · Blog.
Week | Day | Date | Track | Task | What to push / add | Where | Est. hrs | Cut first if short on time? | Done? | Result / URL | Notes
W1 | D1 | 2026-09-08 | Baseline | GSC brand + non-brand export (regex), Generative-AI report, 'video post production' position | Numbers into '06 Baseline · weekly' W1 row | Search Console | 0.5
W1 | D1 | 2026-09-08 | Baseline | Bing Webmaster Tools: verify via GSC import, enable IndexNow, open AI Performance | Citations / cited pages (expect 0) | bing.com/webmasters | 0.3
W1 | D1 | 2026-09-08 | Baseline | GBP Performance 28-day screenshot: views, calls, directions, website clicks, top terms, reviews | Weekly row W1 | business.google.com | 0.2
W1 | D2 | 2026-09-09 | Baseline | Run 14 prompts × 6 engines (84 rows), clean-test hygiene per engine tab | '06 Baseline · AI log' W1 block; screenshots folder | ChatGPT / Perplexity / AIO / AI Mode / Gemini / Copilot | 1.5
W1 | D2 | 2026-09-09 | Baseline | From AI log: list every third-party domain cited for L1-L6 prompts, ranked by frequency | Re-order '05 Citations · list' priority by that list | Sheet | 0.25
W1 | D3 | 2026-09-10 | Citations | Decide canonical name (match signage/invoices); fill NAP master; write 120-word description; pick logo; 6 buyer-language service labels | '05 Citations · NAP master' | Sheet | 0.5
W1 | D3 | 2026-09-10 | Citations | GBP fix: rename (drop '(TLC)'), primary 'Video production service' + up to 9 secondaries, hours Mon-Sat 10-19, description, services list, 20 photos | GBP | business.google.com | 0.75
W1 | D4 | 2026-09-11 | Citations | Bing Places: Import from GBP + auto-sync. Foursquare claim (phone call). Apple Business: start (finish within 14 days) | 3 Tier-0 listings | bingplaces.com · foursquare.com/venue/claim · business.apple.com | 0.75
W1 | D4 | 2026-09-11 | Reddit | Account: founder's personal handle (not a logo account), bio 'Founder, TheLastClicks (Noida) — corporate/wedding films & grading', no link yet. Claim Reddit Pro (free) for keyword alerts: photographer Noida / videographer Delhi / pre wedding Gurgaon. Join the sub list; set user flair in r/videography; read each sub's rules (sheet). Note account age — gate needs ≥30 days | '02 Reddit · subs' Joined? column | reddit.com | 0.5
W1 | D5 | 2026-09-12 | Reddit | Comment-only session: 3-5 specific comments in craft subs (r/videography, r/davinciresolve, r/editors, r/PhotographyIndia) — structure: acknowledge → answer → what we tried → trade-offs. Zero links, zero studio name | '02 Reddit · log' rows | reddit.com | 0.5
W1 | D5 | 2026-09-12 | Quora | Profile: real name, photo, 50-char credential, 4 topic credentials, description with website. Follow 10 topics. Bank questions (sheet pre-filled) | '03 Quora · questions' — mark which 7 | quora.com | 0.5
W1 | D6 | 2026-09-13 | Blog | Author entity: named author page (bio, photo, sameAs → LinkedIn/Instagram/YouTube/Quora/Reddit), Person schema; assign author to all 7 posts | One PR; no date bumps | Admin + repo | 1
W1 | D6 | 2026-09-13 | Blog | Refresh /blog/what-post-production-actually-includes into the hub (capsule, offline/online, conform, correction vs grade, glossary, checklist, internal links) | Publish; GSC request indexing; IndexNow; responsecache:clear | Admin | 1.5
W1 | D7 | 2026-09-14 | Citations | Own profiles: Behance 6 projects (one per vertical, buyer titles), LinkedIn page complete (address, hours, specialties), confirm Facebook URL, Vimeo showcase | 4 profiles with exact NAP | behance · linkedin · facebook · vimeo | 1 | Cut: keep Behance only; LinkedIn/Vimeo → month 2
W2 | D8 | 2026-09-15 | Citations | Udyam MSME registration (30 min). Justdial listing (OTP; live 24-48h). Decline all paid calls | 2 listings | udyamregistration.gov.in · justdial.com | 0.75
W2 | D9 | 2026-09-16 | Citations | Sulekha + IndiaMART seller (6 'products' = 6 verticals, 'ask price') | 2 listings | sulekha.com · seller.indiamart.com | 0.75
W2 | D10 | 2026-09-17 | Citations | WedMeGood free vendor listing + WeddingWire India Lite + WeddingBazaar (NOT ShaadiSaga separately) | 3 listings; 20 images + 2 films each; 'price on request' | wedmegood · weddingwire.in · weddingbazaar | 1
W2 | D10 | 2026-09-17 | Citations | Ask 3 past couples for a review on WedMeGood / WeddingWire (one each, personal message) | Third-party review authority (AI factor #5) | WhatsApp | 0.25
W2 | D11 | 2026-09-18 | Quora | Answer #1 podcast-studio-in-Delhi-NCR thread (50K views, Google #1) — 'what to check in a studio' + disclosure + /industries/podcast. Answer #2 open corporate-video-cost question (0 answers) — drivers only + cost post link | 2 answers; log URLs | quora.com | 1
W2 | D12 | 2026-09-19 | Reddit | Comment session #2: 3-5 value comments; 2 from the thread bank (r/delhi cost-estimate, r/videography corporate panels) with first-person shoot specifics. Still no links, no name | Log | reddit.com | 0.5
W2 | D13 | 2026-09-20 | Blog | Write + publish /blog/what-is-an-aftermovie (capsule, comparison table, on-the-day list, Salesforce/E-Summit examples, brief template link) | Publish; index; IndexNow; cache clear; embed one corporate film | Admin | 2
W2 | D14 | 2026-09-21 | Baseline | Weekly row W2: GSC brand impressions, GBP, listings live count, karma, Quora views | '06 Baseline · weekly' | Sheet | 0.25
W3 | D15 | 2026-09-22 | Citations | Clutch profile (free) + invite 2 corporate clients to review. GoodFirms (categories are permanent — choose once) | 2 listings + 2 review invites | clutch.co/get-listed · goodfirms.co/get-listed | 1
W3 | D16 | 2026-09-23 | Citations | DesignRush + TechBehemoths (Noida page) + Bark profile (never buy leads) | 3 listings | designrush · techbehemoths · bark | 0.75
W3 | D16 | 2026-09-23 | Citations | Shaadidukaan free listing; Weddingz partner form; Canvera email (care@canvera.com) with NAP + portfolio | 3 submissions | shaadidukaan · weddingz · email | 0.5 | Cut → month 2
W3 | D17 | 2026-09-24 | Quora | Answer #3 hourly-rate-for-video-editors (68K views) — drivers + cost post. Answer #4 process-of-video-post-production — link refreshed hub | 2 answers | quora.com | 1
W3 | D18 | 2026-09-25 | Reddit | Comment session #3: r/DesiWeddings + r/noida rec threads — selection criteria and what to ask any vendor, no self-mention yet (gate not met). Check karma: target ≥100 comment karma by D25 | Log; count value vs self-mention | reddit.com | 0.5
W3 | D19 | 2026-09-26 | Blog | Gather original data for locations post: permit status (verify with ASI/DDA), light window, drive time from Sector 26 at 7am, one own frame per place (12-15 photos, alt text) | Data table | Field / Maps | 1
W3 | D20 | 2026-09-27 | Blog | Write + publish /blog/pre-wedding-shoot-locations-delhi-ncr (15 cards + summary table; 'permit/ticketed/free', no ₹) | Publish; index; IndexNow; cache clear; Instagram carousel links post | Admin | 1.5
W3 | D21 | 2026-09-28 | Baseline | Weekly row W3 | Sheet | Sheet | 0.25
W4 | D22 | 2026-09-29 | Citations | Pitch Vidsaga (Delhi video list) + Sloshout (Delhi NCR wedding list, refresh due Oct) + Entrepreneur Hunt (podcast list). 4-sentence pitch each | '05 Roundups & pitches' pitched-on dates | Email / contact forms | 0.75
W4 | D22 | 2026-09-29 | Citations | Real-wedding submissions: WedMeGood (15-20 photos + story) and WeddingSutra (8-10 photos, a DIFFERENT wedding, 90-day exclusivity) | 2 submissions | submissions@wedmegood.com · editor@weddingsutra.com | 0.75
W4 | D23 | 2026-09-30 | Citations | Long tail if time: Sortlist, ProductionHUB, Mappls, Love Stories TV (5 wedding films), Brownbook, IndianYellowPages, Grotal | Listings | various | 0.75 | Cut → month 2
W4 | D24 | 2026-10-01 | Quora | Answer #5 how-to-choose-wedding-photographer-and-videographer (2026-06 activity) — link timeline post. Answer #6 best-pre-wedding-location-Delhi-NCR — link locations post. Stretch #7 best-film-production-house-Noida (evaluate-first + disclosure) | 2-3 answers | quora.com | 1
W4 | D25 | 2026-10-02 | Reddit | GATE CHECK: ≥100 comment karma AND account ≥30 days AND zero removals. If all three: (a) one disclosed comment in a live rec thread ('Full disclosure, I run a studio in Noida — but here's how I'd choose…') and (b) one r/DesiWeddings 'Vendor Post' of recent wedding frames (work, not an ad). If any fails: value-only; graduation moves to month 2 | Log | reddit.com | 0.5
W4 | D25 | 2026-10-02 | Blog | STRETCH: write + publish /blog/how-to-choose-corporate-video-production-company-delhi-ncr. Skip if W3 overran | Publish; index; LinkedIn post of the four questions | Admin | 2 | Cut if W3 overran
W4 | D26 | 2026-10-03 | Baseline | Re-run 14 prompts × 6 engines (84 rows, W4 block). Same hygiene | AI log W4 block | 6 engines | 1.5
W4 | D27 | 2026-10-04 | Baseline | Pull GSC (brand regex + Generative AI), Bing AI Performance, GBP; count live listings; karma; Quora views; pitches replied. Fill month-end row. Write 10-line month-two brief from deltas | Weekly month-end row + brief | Sheet | 0.75
W4 | D28 | 2026-10-05 | Citations | Add all live listing URLs to Organization sameAs (one PR). Store all logins under citations/<platform> | PR + password manager | Repo | 0.5 | Cut → month 2

## 02 Reddit · subs
Week 1-2: comments only, no links. Week 3+: link only when asked or when the blog post is the literal answer. 9:1 ratio forever.
Subreddit | Members | Self-promo rule (short) | Vendor-recommendation asks OK? | Megathread / flair | Karma / age gate | Our use | Joined?
r/delhi | 1,384,905 | Rule 5.2: self-promo only for regular members, 1:10 ratio; 5.1 bans promo/referral codes. Pinned anti-AI-slop rule (29 Jul 2026). | Yes — dozens of photographer/videographer rec threads; flair AskDelhi | Stickied Chat thread; posts often hit modqueue | None stated | PRIMARY. Answer cost-driver and how-to-choose threads with criteria. Self-mention only after gate, disclosed, ≤1 in 10.
r/noida | ~78k | Rule 6: ads/spam removed, repeat = ban. Rule 4: no professional enquiries. | Yes — rec threads exist ('drop the insta handles') | None | None stated | HOME TURF. Comments only; never post a services thread. Self-mention only inside a live rec thread after gate.
r/gurgaon | 167,894 | Rule 4: no promotion of businesses/websites/YouTube/podcasts; no spamming. | Yes (AskGurgaon flair) | None | None stated | Value comments on rec threads (criteria, what to ask a vendor).
r/DesiWeddings | 172,431 | Rule 4: 'Vendor Post' flair allowed ONLY from vendors who participate actively in comments; no promo disguised as review; no promo comments on unrelated posts. | Yes — densest Delhi-NCR photographer-rec venue found | Reviews megathread (independent reviews only, Fridays); Preloved; outfit Mondays | New/low-karma posts not approved | MAIN WEDDING VENUE. W1-W3 comment on rec threads with selection criteria. W4 (after gate): one 'Vendor Post' of recent wedding frames — work, not an ad.
r/IndianWeddings | ~1.4-5k (restricted) | Rule 3: vendors welcome, promo limited to approved threads; work photos OK, ads removed. | Yes but near-dead | None | Restricted — posting needs approval | SKIP this month (PDF listed it; r/DesiWeddings is the live one).
r/videography | 455,504 | Rule 2: no self-promotion, sales, advertising; astroturfing = permanent blacklist. Rule 4: hiring posts must state budget, dates, country. | Hiring posts only with budget | Monthly camera-buying megathread; posts without user flair held for review | Set a user flair first | CRAFT VENUE. Answer corporate-event workflow, wedding-video pricing-logic, aftermovie critique threads. Never mention services.
r/VideoEditing | 526,334 | Rule 7: advertising services = IMMEDIATELY bannable. Rule 5: no rates questions. 10:1 reddiquette. | No | Monthly feedback/software/hardware; Tutorial Tuesdays | None stated | Hobbyist. Craft answers only (workflow, codecs, proxies). Zero studio talk.
r/editors | 195,747 | Rule 7: advertising services = spam. | No | — | None stated | Pro editors. Craft answers; peer credibility.
r/davinciresolve | ~230k | Rule 3: not a marketplace — selling LUTs/services removed. Rule 10: job posts need rate + hours. | N/A | Hardware megathread; FAQ Friday; monthly tools thread | AutoMod asks system/version | GRADING EXPERTISE. Answer wedding-grade / 4:2:2 / skin-tone threads with node-level specifics.
r/colorists | 68,727 | Rule 7: no self-promotion ('room of doctors'). Rule 6: no rates. Rule 9: no shorteners/affiliate links. | No | Monthly tools thread | None stated | Peer venue; feedback posts need before/after + node tree. Comments only.
r/PhotographyIndia | ~111k | Rule 7: no promotions. Rule 5: no sale posts. Rule 3: OC only with gear in title. | Buying-advice posts need budget | None | None stated | MOST ACTIVE INDIAN PHOTO SUB. Post 1-2 OC frames (gear in title) per month; answer craft threads.
r/photography | ~5.6M | Rule 4: self-promo ≤10% and only in weekly community threads. Rule 5: hiring → r/PhotographyJobs; pricing → sticky Official Question thread. Rule 10: no AI text. | Pricing only in sticky | Official Question thread (sticky); weekly threads | None stated | Low priority; answer in the sticky when a question matches.
r/WeddingPhotography | ~81k | Rule 1: no blog/self-promo posts. Rule 4: couples' questions only in weekly 'ask a wedding photographer' thread. | Couples only in weekly thread | Weekly ask thread; sharing threads | None stated | Peer venue. Answer in the weekly thread (timeline, haldi light, backup audio).
r/AskPhotography | ~753k | Rule 8: no monetised links. Rule 9: no spam. Titles must end in '?'. | Business/Pricing flair exists | None | None stated | Craft answers; Business/Pricing flair threads are cost-driver questions.
r/indianstartups | ~128k | Rule 2: no direct sales/ads/promo; self-promotion = anything you have a stake in. | Yes — 'reliable video production agency' rec threads exist | None | None stated | Brand-video buyers. Value comments: how to brief, how to compare quotes.
r/smallbusinessindia | ~116k | Rule 1: 9:1 rule hard-coded. Rule 3: no external links/social handles. Rule 5: data collection = serious offence. | Product/brand talk via flairs | None | None stated | Comment on 'how much should a corporate video cost' style threads — drivers only, no links ever.
r/podcasting | ~191k | Rule 1/2: promo only in weekly threads (episodes Thu, products/services Wed 7am ET). Rule 9: affiliated users MUST disclose. | Jobs → Tuesday thread | Thu episode; Wed product/service; Tue jobs; Fri trailer | AutoMod removes karma <5 or account <7 days | Craft comments (multi-cam, audio). Month 2: one disclosed post in the Wed product/service thread.
r/Filmmakers | 3,074,253 | Rule 2: creative posts need 100-char submission statement; posting your film for views not allowed. Rule 6: no GenAI work. | Hiring via 'Looking for Work' flair | Megathread Monday; Sharing Saturday | None stated; verified-pro flair available | Comments only. Month 2: Sharing Saturday for one brand film with statement.
r/india | 3,482,630 | Rule 9: 1:10 self-promo tolerance, contact mods first. Rule 10: no AI content. Rule 11: AskIndia only in weekly thread. | Only in weekly AskIndia thread | Weekly AskIndia; Mental Health | None stated | Low priority. Skip unless a weekly-thread question matches exactly.
r/youtubeindia | — | — | Editor-rate threads exist | — | — | One value comment on the 'how much to pay an editor' thread (drivers, no ₹).
r/AskIndia · r/indiasocial · r/marketing · r/ghaziabad | — | AskIndia: no professional advice requests. indiasocial: no promo, no freelancing/client-hunting. marketing: zero tolerance, 30 days + 300 karma gate. ghaziabad: ~5k, no rules, dead. | No | — | r/marketing: 30d / 300 karma | SKIP this month.
r/DelhiFreelancers · r/IndieFilmIndia · r/IndianPhotography | do not exist | — | — | — | — | Do not exist (checked against subreddit index). r/indianFilmmakers (95), r/IndianFilmPros (50), r/FreelanceIndia (556), r/DelhiNCR (142) exist but are inactive.

## 02 Reddit · threads
URL | Sub | Date | Title / ask | Engagement | Why it matters | Action (comment / watch / skip) | Done? | Our comment URL
https://www.reddit.com/r/delhi/comments/1sn6d5y/ | r/delhi | 2026-04-16 | Photographer wedding cost estimate | 4↑ / 9c | Recent, pure cost-driver question | Comment: the 5 drivers, what to ask; no ₹, no link
https://www.reddit.com/r/delhi/comments/1s5zljj/ | r/delhi | 2026-03-28 | How do you choose the best wedding photographer in Delhi? (Need advice) | 1↑ / 3c | 'How to choose' intent — ideal for a specifics-heavy answer | Comment: 4 checks (named crew, backup audio, full-gallery sample, contract terms)
https://www.reddit.com/r/delhi/comments/1sij72e/ | r/delhi | 2026-04-11 | Wedding Photographers Leads | 3↑ / 3c | 'No reels, just one simple video' — budget-documentary segment | Comment: what a one-camera documentary edit actually needs
https://www.reddit.com/r/DesiWeddings/comments/1sc2uio/ | r/DesiWeddings | 2026-04-04 | Delhi wedding photo and videography suggestions for December 2026 wedding | 3↑ / 9c | Explicitly 'more particular about the video'; wedding is still ahead | Comment: how to judge a wedding filmmaker (audio, multi-cam, sample of a full ceremony, not a trailer). W4 gate → disclosed mention allowed
https://www.reddit.com/r/DesiWeddings/comments/1srpygh/ | r/DesiWeddings | 2026-04-21 | Suggest some good photographers / pre-wedding shoot in Delhi NCR | 1↑ / 3c | Pre-wedding; 'personal experience' wanted | Comment: location + light + permit reality (feeds W3 post). Link the post only if asked
https://www.reddit.com/r/DesiWeddings/comments/1n34y6v/ | r/DesiWeddings | 2025-08-29 | Looking for wedding photographers in Gurgaon | 2↑ / 7c | Budget stated | Watch; comment with criteria if still active
https://www.reddit.com/r/noida/comments/1q2t605/ | r/noida | 2026-01-03 | Looking for a wedding photographer for a small wedding in Noida | 2↑ / 4c | Home turf | Comment: small-wedding coverage plan (what one photographer + one filmmaker can cover). W4 gate → disclosed mention
https://www.reddit.com/r/noida/comments/1fu7xjs/ | r/noida | 2024-10-02 | Wedding Photographer Recommendations pls | 9↑ / 13c | Highest-engagement Noida rec thread; likely ranks | Old — read for what people asked; do not necro-comment
https://www.reddit.com/r/gurgaon/comments/1ry6gmd/ | r/gurgaon | 2026-03-19 | Looking for a videographer / content creator in Gurgaon for a short lifestyle shoot | 1↑ / 0c | Unanswered brand-content demand | Comment: what a half-day lifestyle shoot needs (crew, looks, deliverables); no link
https://www.reddit.com/r/delhi/comments/1ojop97/ | r/delhi | 2025-10-30 | Looking for a Delhi-based creative agency (in-house video, reels) | 1↑ / 1c | Corporate/brand video buyer | Comment: agency vs studio vs freelancer trade-offs (feeds W4 post)
https://www.reddit.com/r/indianstartups/comments/1rf64ei/ | r/indianstartups | 2026-02-26 | Recommendations for a reliable video production agency in Bangalore? | 1↑ / 0c | D2C brands ask here; only reply was an undisclosed plug | Comment: how to brief and compare quotes; no mention (wrong city)
https://www.reddit.com/r/videography/comments/1ogoh5j/ | r/videography | 2025-10-26 | Wedding Video Price | 11↑ / 29c | Pricing-logic thread AI engines pull from | Comment: cost drivers from the studio's side (crew, cameras, audio, edit hours) — no ₹
https://www.reddit.com/r/videography/comments/1qtyzux/ | r/videography | 2026-02-02 | New video business hired by a corporate client to cover two 90-min panels | 9↑ / 24c | Corporate-event workflow Q&A | Comment: run-of-show, desk audio + room backup, IMAG, deliverables
https://www.reddit.com/r/videography/comments/1pmb5qw/ | r/videography | 2025-12-14 | First video ever for a corporate event… | 30↑ / 25c | Aftermovie / corporate critique venue | Comment: aftermovie vs highlight structure (feeds W2 post)
https://www.reddit.com/r/davinciresolve/comments/1ucf8vb/ | r/davinciresolve | 2026-06-22 | Is editing in 4:2:2 worth the expense for wedding videography? | 1↑ / 37c | Grading expertise showcase | Comment: where 4:2:2 actually pays (mixed haldi light, skin tones), node approach
https://www.reddit.com/r/davinciresolve/comments/1lz8nhl/ | r/davinciresolve | 2025-07-14 | How to fix my best friend's wedding video | 71↑ / 60c | High-traffic wedding-grade thread | Comment if still open: correction-first recipe
https://www.reddit.com/r/youtubeindia/comments/1vwwe5a/ | r/youtubeindia | 2026-08-24 | How much should I pay an editor in India for 10-30 min vlogs? | 3↑ / 15c | Editing-rate benchmark thread | Comment: what drives editor cost (footage ratio, revisions, motion graphics) — no ₹
https://www.reddit.com/r/delhi/comments/1k26je3/ | r/delhi | 2025-04-18 | Where can I buy studio/podcast equipment offline… | 1↑ / 5c | Only podcast-adjacent Delhi thread; no 'video podcast studio Delhi' thread exists | Gap: month 2, ask a genuine non-promotional question in r/podcasting or r/delhi about multi-cam podcast setups in NCR
— | r/videography | — | No India-angle concert / live-music videographer thread exists; no 'is X studio legit' Delhi thread exists | — | Open slots | Month 2: a well-framed question post can own them (not this month — gate)

## 02 Reddit · log
Log every contribution. Count value-only vs self-mention rows — self-mentions must stay ≤ 1 in 10.
Date | Sub | Thread URL | Type (comment / post / answer) | Value-only or self-mention? | Link included? | Upvotes after 48h | Removed? (why) | Notes

## 03 Quora · questions
URL | Question | Bucket | Followers / answers | Recent? | Ranks on Google? | Link to use (only if it truly answers) | Week | Answered? | Answer URL | Views @ 30d
https://www.quora.com/Im-looking-to-start-a-podcast-in-Delhi-NCR-and-I-need-a-great-studio-Are-there-any-recommendations | Start a podcast in Delhi NCR — need a great studio, recommendations? | Podcast | 1 / 2 · 50K views | 2025-06 | Google #1 for 'podcast studio delhi' query | /industries/podcast (only after 'what to check in a studio' is answered) | W2
https://www.quora.com/How-much-do-corporate-video-production-services-cost | How much do corporate video production services cost? | Corporate cost | 2 / 0 — OPEN, no answers | none | unverified | /blog/video-editing-cost-india or /blog/how-to-brief-a-video-production-team | W2
https://www.quora.com/What-is-the-hourly-rate-for-video-editors-in-India | Hourly rate for video editors in India? | Editing rates | 20 / 6 · 68K views · 57 upvotes | 2022-08 | unverified | /blog/video-editing-cost-india | W3
https://www.quora.com/What-is-the-process-of-video-post-production | What is the process of video post-production? | Post-production | 2 / 3 · 1.6K | 2021-10 | unverified | /blog/what-post-production-actually-includes (refreshed W1) | W3
https://www.quora.com/How-do-I-choose-a-good-wedding-photographer-and-videographer | How do I choose a good wedding photographer and videographer? | Choose | 7 / 7 · 386 | 2026-06 | unverified | /blog/wedding-photography-timeline-planning | W4
https://www.quora.com/Which-is-the-best-pre-wedding-shoot-location-in-Delhi-NCR-India | Best pre-wedding shoot location in Delhi NCR? | Pre-wedding | 1 / 2 · 376 | 2024-06 | unverified | /blog/pre-wedding-shoot-locations-delhi-ncr (published W3) | W4
https://www.quora.com/Which-is-the-best-film-production-house-in-Noida | Best film production house in Noida? | Best companies | 4 / 2 · 38K views | ≤2025 | unverified | None in body. 'How to evaluate' answer + one-line disclosure naming the studio. Stretch answer #7. | W4
https://www.quora.com/How-much-does-a-pre-wedding-shoot-cost-in-india | Pre-wedding shoot cost in India? | Pre-wedding | 41 / 14 · 26K | 2026-05 | unverified | Drivers only; link locations post | M2
https://www.quora.com/How-much-can-a-corporate-video-shooting-for-2-minutes-cost | 2-minute corporate video shoot cost? | Corporate cost | 8 / 3 · 6.4K | 2017 | unverified | /blog/video-editing-cost-india | M2
https://www.quora.com/How-much-does-it-actually-cost-to-make-a-corporate-film | What does a corporate film actually cost? | Corporate cost | 2 / 4 · 1K | 2021-06 | unverified | /blog/how-to-brief-a-video-production-team | M2
https://www.quora.com/How-much-does-an-ad-film-production-cost | Ad film production cost? | Brand film | 4 / 3 · 7.4K · 12 upvotes | 2021-04 | unverified | /services/videography (only if drivers answered) | M2
https://www.quora.com/What-should-professional-video-editors-charge-for-10-minute-videos-in-India | What should editors charge for 10-minute videos in India? | Editing rates | 3 / 3 · 22.6K · 17 upvotes | 2019 | unverified | /blog/video-editing-cost-india | M2
https://www.quora.com/How-can-I-book-a-podcast-studio-in-Delhi | How can I book a podcast studio in Delhi? | Podcast | 1 / 1 · 32K | 2024-07 | unverified | /industries/podcast | M2
https://www.quora.com/What-is-the-ideal-duration-for-a-real-estate-video-or-walk-through-video | Ideal duration for a real-estate walkthrough video? | Real estate | 4 / 5 · 887 | 2026-08 | unverified | /industries/real-estate | M2
https://www.quora.com/Which-are-the-best-budget-wedding-photographers-in-Delhi-for-a-budget-of-around-1-5-lakhs-for-2-days | Best budget wedding photographers in Delhi (~1.5L, 2 days)? | Wedding cost | 42 / 10 · 6.5K | 2022-06 | unverified | How-to-evaluate answer; disclosure; no price talk | M2
https://www.quora.com/Who-are-the-best-wedding-photographers-available-in-Delhi-NCR-on-a-limited-budget | Best wedding photographers in Delhi NCR on a limited budget? | Wedding cost | 2 / 3 · 1.5K | 2026-04 | unverified | Same as above | M2
https://www.quora.com/Who-is-the-best-Wedding-photographers-in-Delhi-NCR-Noida | Best wedding photographers in Delhi NCR / Noida? | Photographers Noida | 31 / 1 · 1.9K | 2021-08 | unverified | Evaluate-first answer + disclosure | M2
https://www.quora.com/In-film-post-production-what-does-grading-mean | In film post-production, what does grading mean? | Colour | 6 / 2 · 6.4K | 2019 | unverified | /blog/what-post-production-actually-includes | M2
https://www.quora.com/Which-is-the-best-video-production-company-in-Delhi-NCR | Best video production company in Delhi NCR? | Best companies | 8 / 2 · 521 | 2023-05 | unverified | Evaluate-first; disclosure | M2
https://www.quora.com/Who-is-the-best-corporate-film-makers-and-video-production-company-in-Delhi | Best corporate film makers / video production company in Delhi? | Best companies | 5 / 6 · 920 | ≤2025 | unverified | Evaluate-first; disclosure | M2
https://www.quora.com/Where-are-the-best-places-in-Delhi-for-pre-wedding-shoots | Best places in Delhi for pre-wedding shoots? | Pre-wedding | 1 / 3 · 1K | 2019 | unverified | /blog/pre-wedding-shoot-locations-delhi-ncr | M2
https://www.quora.com/What-do-videographers-typically-charge-to-shoot-a-music-video-for-independent-musical-artists | What do videographers charge for an indie music video? | Concert/music | 4 / 11 · 4K | ≤2025 | unverified | /industries/cover-artist page (public label: live music films) | M2
https://www.quora.com/What-is-the-cost-of-making-a-decent-music-video-in-India-if-the-song-is-good-My-max-budget-is-Rs-30000-Would-production-houses-contribute-some-percentage-from-their-end-if-they-find-the-content-good | Cost of a decent music video in India (₹30K budget)? | Concert/music | 4 / 2 · 29K | 2023-03 | Google #1 for 'music video production cost india' | Drivers only; honest about what a small budget buys | M2
https://www.quora.com/What-equipment-is-needed-to-set-up-a-video-studio-for-producing-high-quality-video-podcasts | Equipment for a high-quality video podcast studio? | Podcast | 13 / 4 · 2.6K | ≤2025 | unverified | /industries/podcast | M2
https://www.quora.com/Who-are-some-great-wedding-videographers-in-India | Great wedding videographers in India? | Choose | 8 / 3 · 2.2K | 2022-07 | unverified | Evaluate-first; disclosure | M2

## 03 Quora · rules & template
Item | Detail
State of Quora, Sep 2026 | ~300M visits/month and falling ~6%/month (Similarweb Jul 2026); India = 10.3% of traffic (#2 country), not the 25% in old decks. Still cited: #6 domain in Google AI Overviews at 4.7% (Ahrefs Sep 2026), #4 in AI Mode at 7.25% of responses (Semrush Oct 2025), in 32% of Google 'Discussions and forums' modules (Ahrefs Aug 2026). Quora auto-posts AI 'Assistant' answers (Sept 2025 batch, ~1 view each) — a credentialed human answer outranks them.
What gets cited | Semrush: ~90% of AI-cited Quora answers carry the 'Most Relevant' label (9x more likely); cited threads avg 37 replies / 15 upvotes; short paragraphs, logical order; only ~10% keyword overlap with the prompt — topical relevance, not exact match.
Profile — name | Real name. Real photo.
Profile — credential (first ~50 chars shown beside answers) | Founder, TheLastClicks — video & photo studio, Noida · [N] yrs. Must be literally true. No URLs in credentials.
Profile — topic credentials | One per bucket, quantified and true: Wedding Photography ('Shot [N]+ weddings across [N] Indian cities'); Video Editing / Post-Production ('In-house DaVinci grade and mix, [N] films'); Corporate Video ('Event films for Salesforce, Tata Tea, …' — only clients cleared for public naming); Podcasting ('Multi-cam podcast video for [N] shows').
Profile — description | 3 lines: what the studio does in buyer language, city, website URL (allowed in description). Same NAP as everywhere.
Spaces | Do NOT create a Space (needs weekly posting to pay off). Do not join-and-spam existing ones this month.
Policy — self-promotion (quoted) | 'Self-promotion in answers is permitted only in the context of a helpful, and direct response, otherwise it is considered to be spam.' 'Self-promotional links that do not form a part of a direct and helpful response to the question are not allowed.' 'Affiliate links are not allowed.' (help.quora.com/hc/en-us/articles/115004211543)
Policy — disclosure (quoted) | 'Answers promoting products or services must include a disclosure of any affiliations that might inform the answer's interpretation.' 'When in doubt … disclose it.' (help.quora.com/hc/en-us/articles/360055133711)
Policy — credentials (quoted) | 'Credentials must be true and helpful … describe a personal connection to a topic.' Non-compliant credentials are hidden. (help.quora.com/hc/en-us/articles/360057638052)
Collapse / ban triggers | Duplicate answers by the same writer across merged questions; mostly-images; not answering; very short; >~20% of answer as links; 10+ answers/hour ('artificial engagement'); AI-written text (Pangram detection). Moderation is automated first-pass; appeal to a human.
Cadence | Max 2-3 answers per session, 1 session/week. 7 answers this month. Never answer 10+/hour.
Links | One link max, contextual, only when the post is the literal next step. Nofollow anyway. Prefer a blog URL over the homepage. Never a phone number or 'contact us'.
Prices | Never rupee figures or ranges (studio rule + it dates fast). Drivers, trade-offs and what to ask a vendor. Consistent with /blog/video-editing-cost-india.
'Best X in Noida' questions | Answer with how to evaluate (3-4 checks), then one-sentence disclosure naming the studio. Never a bare 'we are the best'. These are the answers AI Overviews lift for local prompts.
Answer template (150-300 words) | 1) Direct answer in 2-3 sentences with a concrete specific (camera count, crew roles, deliverable list) — this is what AI engines lift. 2) Three bullets, each one driver with a real example from a shoot. 3) Two sentences of advice the reader can act on tomorrow (what to ask a vendor). 4) 'Disclosure: I run a video/photo studio in Noida (TheLastClicks), so I'm biased toward …' + optional single link.
Example — post-production question | 'Post-production is everything between the last shot and the delivered file: offline edit for structure, online/conform for resolution and graphics, colour correction then grade, sound edit and mix, and mastering per platform. On a typical brand film it is about half the labour.' → bullets: offline vs online (why a rough cut looks 'wrong'), correction vs grade (skin tones first, look second), masters per platform (IG 9:16, broadcast-safe, archival). → advice: ask for the deliverables list before the quote. → Disclosure + link to the hub post.
Story bank (real shoots to draw on) | Haldi light problem (mixed colour temps, yellow cast on skin); desk-audio + room backup at a live concert (Sonu Nigam / Hariharan / Shankar Mahadevan films); the pour at high frame rate (Tanqueray / Johnnie Walker bottle films); run-of-show coverage at a summit (Salesforce, E-Summit 2025); walkthrough as space not slideshow (CapitaLand, DLF, TaskUs); multi-cam podcast cut into episode + month of clips. Name clients only where public use is cleared.
Measure | Log answer URL + views at 30 days in the questions tab. Month-end: total views, upvotes, whether any answer got the 'Most Relevant' label, whether any answer appears in the W4 AI log.

## 04 Blog · calendar
Week | Kind | URL / slug | Working title | Target queries | Why (evidence) | Answer capsule (40-60 w) | Outline (H2s) | Internal links | Evidence to add | Length | Hard rules | Companion / distribution | Est. hrs | Published? | Indexed? (GSC) | Cited by AI? (W4 check)
W1 | Refresh (existing) | /blog/what-post-production-actually-includes | What video post-production actually includes: offline edit, online, conform, grade, mix, masters | video post production; what is post production in video; offline vs online edit; colour correction vs colour grading; what is a conform; what is a DIT | Site already registers for 'video post production' at GSC pos 57-64 with no supporting content. 'What is / how does' queries carry 89.3% AI citation rate (Semrush Jun 2026). Upgrade, don't duplicate (Google AI guide: no page per variation). | 40-60 words under H1: 'Post-production is everything between the last shot and the delivered file: the offline edit (structure), the online/conform (resolution, graphics), colour correction then grade, sound edit and mix, and mastering per platform. On a typical brand film it is roughly half the labour.' | H2 Offline edit (rough cut -> fine cut) ¦ H2 Online edit & conform (what 'conform' means) ¦ H2 Colour: correction vs grading (two passes) ¦ H2 Sound: dialogue clean-up, music, design, loudness standards ¦ H2 Masters & deliverables (IG 9:16, broadcast-safe, archival) ¦ H2 Who does what: editor, colourist, sound designer, DIT ¦ H2 Glossary (10 terms, one line each) ¦ H2 What to send your post team (checklist) | /services/post-production; /blog/video-editing-cost-india; /blog/how-to-brief-a-video-production-team; /industries/corporate-shoots | 1-3 sourced facts (e.g. loudness standard -14 LUFS for YouTube / -23 LUFS EBU R128 for broadcast; DaVinci Resolve node-based grading). One named quote from the founder as a pull-quote. | 1,000-1,400 words (Ahrefs: median cited page 1,115 words; length corr 0.04 — don't pad) | No rupee figures. No turnaround promises ('in days'). Byline = founder real name + author page. Real 'Updated' date only because content substantively changed. | 60-90s YouTube explainer 'offline vs online edit' (optional, feeds Week 3 YouTube track); Quora answer to 'what does post production include' links here. | 2
W2 | New | /blog/what-is-an-aftermovie | What is an aftermovie? Aftermovie vs highlight film vs full event record | what is an aftermovie; aftermovie vs highlight video; event aftermovie production; corporate event aftermovie India; conference aftermovie | Zero Indian pages rank for 'aftermovie' (SERP is Dutch/Belgian agencies). Comparison pages have the highest citation rate (1.87x, Delta V Apr-Jul 2026) and 2.4x more brand mentions (Semrush). | 'An aftermovie is a 60-180 second film released after an event that sells the next edition: energy, scale, speakers, crowd. A highlight film documents this edition for attendees; a full record is the archival multi-cam cut. Most corporate events need two of the three.' | H2 Definition (capsule) ¦ H2 Comparison table: aftermovie / highlight film / full record / social cutdowns — purpose, length, audience, cameras, audio, release timing (no durations promised) ¦ H2 What an aftermovie needs on the day (b-roll list, crowd releases, speaker soundbites, drone permission) ¦ H2 Where it goes wrong (no audio backup, no brand-safe shots, legal review) ¦ H2 Examples from our work (Salesforce Bengaluru aftermovie, E-Summit 2025 — describe, no invented numbers) ¦ H2 Brief template (link) | /industries/corporate-shoots; /blog/corporate-event-video-coverage-guide; /blog/photo-vs-video-corporate-event-coverage; /services/videography | One stat on event video ROI from a named source; one quote from an event-marketing client (existing testimonial: Priya Mehta, Marketing Head) if permission exists. | 900-1,300 words + one table | No prices. No 'delivered in X days'. Use buyer words: 'corporate event aftermovie', never internal labels. | Embed one existing corporate aftermovie (YouTube) as media item; Quora answers on 'event video coverage' link here. | 2
W3 | New (original local data) | /blog/pre-wedding-shoot-locations-delhi-ncr | Pre-wedding shoot locations in Delhi NCR: 15 places, permits, best light, distance from Noida | pre wedding shoot locations delhi ncr; pre wedding shoot locations noida; pre wedding shoot places in delhi; best pre wedding locations gurgaon | Evergreen listicle query; every ranking page is a 2025/2026-dated list refreshed yearly. Commercial queries cite listicles 37.6% (Position.digital). SEJ Jul 2026: 'original local data' is what gets local businesses cited. | 'Fifteen Delhi NCR pre-wedding locations we have actually shot, grouped by look (heritage, garden, urban, water, night), each with permit status, best light window, crowd level and drive time from Noida.' | H2 How we chose these (shot there, not scraped) ¦ H2 Noida & Greater Noida (Okhla Bird Sanctuary, Botanical Garden, Sector 150 green belt, Greater Noida expressway, Buddh circuit area) ¦ H2 Delhi heritage (Humayun's Tomb, Qutub, Agrasen ki Baoli, Sunder Nursery, Lodhi Garden) ¦ H2 Delhi urban/night (Hauz Khas, CP, Yamuna Ghat) ¦ H2 Gurgaon & Faridabad (Aravalli Biodiversity Park, Damdama Lake, Sohna, Surajkund) ¦ H2 Permit & fee reality (state 'permit required / ticketed / free' — verify each with ASI/DDA before publishing; no ₹ amounts) ¦ H2 Best light per location (golden hour direction) ¦ H2 Packing & timing checklist ¦ Per-location card: look, permit status, light, crowd, drive time from Sector 26, our sample frame | /industries/wedding-pre-wedding; /blog/wedding-photography-timeline-planning; /services/photography; /contact | Original data = the differentiator: drive time from Sector 26 (Google Maps at 7am), permit status verified this month, light direction. 12-15 own photos with descriptive alt text and geo in caption (not EXIF). | 1,400-1,800 words (list format); one table summarising all 15 | No entry-fee rupee amounts (they go stale and violate no-public-pricing rule) — say 'ticketed' / 'permit'. No package prices. Refresh annually (put 'Updated' date; re-verify permits). | Instagram carousel of the 15 frames -> links post; Quora answers to 'pre wedding locations Delhi' link here (this is the honest answer). | 2.5
W4 | New (stretch — drop if W3 overruns) | /blog/how-to-choose-corporate-video-production-company-delhi-ncr | How to choose a corporate video production company in Delhi NCR (and the four questions that expose a weak one) | how to choose a video production company; corporate video production company delhi ncr; questions to ask a video production company; in-house vs agency video production | Only filmgoi.com has an India version; how-to pages cite ~68% (Averi, directional); comparison table adds the 1.87x rate format. Feeds the 'best video production Delhi NCR' AI answers with a non-listicle source. | 'Choose on four things: who actually shows up on the day (named crew, not a roster), whether post is in-house, how they handle brand/legal review, and whether they can show a film that solved a brief like yours. Price bands matter less than scope fit.' | H2 The four questions ¦ H2 Comparison table: freelancer / small studio / ad agency-led / large production house — best for, risks, who owns the edit, revision handling ¦ H2 Red flags in a quote ¦ H2 What a good brief does to the price (link cost drivers post) ¦ H2 Checklist to download/copy | /blog/how-to-brief-a-video-production-team; /blog/video-editing-cost-india; /services/videography; /industries/corporate-shoots; /portfolio | One sourced stat on video in B2B marketing; one client quote. | 1,000-1,300 words + table | No prices, no timelines. Don't name competitors negatively. | LinkedIn company-page post summarising the four questions; Reddit r/videography answer if a fitting thread exists (no link unless asked). | 2

## 04 Blog · rules
# | Standing rule
1 | Answer capsule (40-60 words) directly under H1 — ~44% of AI citations come from the first third of the page.
2 | Headings phrased as the sub-questions people ask (fan-out): 'What is X', 'X vs Y', 'What does X include'.
3 | 1-3 sourced statistics or a named quote per post (Princeton GEO: +30-40% visibility from stats/quotes/citations).
4 | Byline with the founder's real name; author page with background; Person schema sameAs -> LinkedIn, Instagram, YouTube, Quora, Reddit.
5 | Real published/updated dates only. Never bump a date without substantive change (Google helpful-content doc).
6 | No rupee figures anywhere. No turnaround/delivery-time promises. Cost = drivers only.
7 | Buyer language in titles/H1: 'corporate event aftermovie', 'wedding film', 'live concert film' — never 'alcobev', 'cover artist'.
8 | Every post links: one service page + one industry page + one sibling post. Every service/industry page links back to the relevant post.
9 | Length is not a factor (Ahrefs: corr 0.04). Stop when the question is answered. Median cited page ≈1,100 words.
10 | One post per week maximum. Three-plus posts a day = scaled-content pattern (see mayhighfilms.com) and Google's Aug 2026 spam policy.
11 | After publishing: request indexing in GSC, submit via Bing IndexNow, add to Quora answer bank as the link for matching questions.
12 | After any deploy touching public/build: run responsecache:clear (repo rule) or cached HTML 404s its own CSS.

## 05 Citations · list
Tier | Week | Platform | URL | Cost | Verification | Link type | Category to pick | Priority | Action / notes | Status (todo / submitted / live / rejected) | Live listing URL | Date live
0 Maps/engines | W1 | Google Business Profile — fix, not claim | https://business.google.com | Free | Already verified | Website (nofollow) | Primary: Video production service · Secondary: Photography studio, Photographer, Commercial photographer, Film production company, Video editing service, Wedding photographer, Media company | P0 | Rename to canonical name (no '(TLC)'). Set 10 categories max. Add hours Mon-Sat 10-19, description, 20+ photos, services list, website UTM. Incorrect primary category = #1 negative local factor.
0 Maps/engines | W1 | Bing Places for Business | https://www.bingplaces.com | Free | Import from GBP -> phone/email OTP instant; else postcard 1-2 wks | Website (nofollow) | Mirror GBP | P0 | Feeds ChatGPT/Copilot. Use 'Import from Google Business Profile' + enable auto-sync. Reviews don't transfer.
0 Maps/engines | W1 | Apple Business (ex Business Connect) | https://business.apple.com/business-connect/ | Free | Documents/domain/phone; finish within 14 days of starting | Website | Video production / Photographer | P1 | Business Connect merged into 'Apple Business' 14 Apr 2026; India supported. Add logo, hours, photos.
0 Maps/engines | W1 | Foursquare Places (claim) | https://foursquare.com/venue/claim | Free (optional $20 instant) | Phone call to business number | None public | Photography studio / Video production | P0 | No public page since 2025, but Foursquare POI data is an OpenAI partner (Dec 2024) — ChatGPT grounds local intent on it. Claim + NAP exact.
0 Maps/engines | W2 | Mappls (MapmyIndia) | https://www.mappls.com/add-a-business | Free | Unverified | Website field | Photography / video | P2 | Generates Mappls Pin; add phone, website, category, photos.
1 India directories | W2 | Justdial | https://www.justdial.com (List your Business) | Free; paid priority optional — decline | Mobile OTP; live 24-48 h | Website field (assume nofollow) | Photographers; Video Shooting Services; Corporate Video Makers | P0 | DA ~74. Competitors (The Studio Clicks 555 reviews) live here — brand-confusion risk; get listed with exact NAP + logo.
1 India directories | W2 | Sulekha | https://www.sulekha.com/list-your-business | Free profile; leads paid — decline | Mobile OTP | Website (nofollow) | Photographers / Videographers / Corporate video | P1 | Ignore lead-package sales calls.
1 India directories | W2 | IndiaMART (seller) | https://seller.indiamart.com | Free; TrustSEAL paid — decline | Phone OTP; docs (GST/Udyam) for verified badge; min 3 services | Website on company page (nofollow) | Video Production Service; Corporate Video Service; Product Video Service; Event Photography Service | P1 | Ranks for 'post production company delhi', 'product photography noida'. Add 6 'products' = 6 verticals in buyer language. No ₹ in listings (mark 'Ask price').
1 India directories | W3 | Bark.com India | https://signup.bark.com/photography/ | Free profile; pay-per-lead — don't buy | Email/phone | Public company profile page | Videographer / Commercial photographer | P2 | India pages indexed; profile page is a citation even without buying leads.
1 India directories | W3 | Brownbook | https://www.brownbook.net/ | Free | Email (unverified) | Website field | Photography | P3 | Live, 44M listings. 10 min.
1 India directories | W3 | IndianYellowPages | https://www.indianyellowpages.com/ | Free | Unverified | Website field | Services -> Photography/Video | P3 | 10 min.
1 India directories | W3 | Grotal | https://www.grotal.com/ | Free | Unverified | — | Photographers in Noida | P3 | DA ~47.
1 India directories | W4 | ExportersIndia | https://www.exportersindia.com/register-business-online | Free | Phone/email (unverified) | Website field | Services -> Photography | P3 | Only if time remains.
1 India directories | W4 | TradeIndia | https://www.tradeindia.com | Limited free | Phone/email (unverified) | Website field | Video production services | P3 | Only if time remains; heavy upsell.
1 India directories | — | Hotfrog / Cylex / Yalwa / AskLaila | hotfrog.in · cylex.in · yalwa.in · asklaila.com | Free | Unverified (fetch blocked) | — | — | P4 | Month 2 backlog. Tuugo.in is DEAD (parked) — skip. Yelp India does not exist — skip. Nextdoor: no India — skip.
2 Wedding platforms | W2 | WedMeGood | https://www.wedmegood.com/vendor-signup | Free listing (Premium ₹50-85k/yr — decline for now) | Email + phone | Profile page | Wedding Photographers; Wedding Videography | P0 | Most-cited Indian wedding domain. Portfolio 20+ images, 2 films, service area, 'price on request' (no ₹ on public profile). Ask 3 past couples to review here.
2 Wedding platforms | W2 | WeddingWire India | https://www.weddingwire.in/emp-Acceso.php | Free 'Lite' | Phone/email | Storefront | Wedding Photographers (+ Videography) | P0 | weddingwire.in/wedding-photographers/noida ranks for the Noida query. Reviews here count as third-party review authority (AI factor #5).
2 Wedding platforms | W2 | WeddingBazaar (Matrimony.com; absorbed ShaadiSaga) | https://www.weddingbazaar.com/vendor-signup | Free listing | Phone | Profile | Photographer | P1 | Do NOT list on ShaadiSaga separately — it is now 'WeddingBazaar Partners'.
2 Wedding platforms | W3 | Shaadidukaan | https://www.shaadidukaan.com/free-listing | Free | Call-back verification | Website field | Photographers | P2 | Ranks for 'candid wedding photographer noida price'.
2 Wedding platforms | W3 | Weddingz.in (OYO) | https://weddingz.in/partner-with-us/ | Free (unverified) | — | Profile | Photographers | P2 | No videographer category; list as photographer.
2 Wedding platforms | W3 | Canvera | email care@canvera.com | Free (unverified) | Email | Directory profile | Photographers | P2 | Email with NAP + portfolio link.
2 Wedding platforms | W4 | Sloshout · TheWeddingCompany | info@sloshout.com · theweddingcompany.com/wedding-photographers/noida | Unverified | Email | — | Wedding photographers Noida | P3 | Both rank for the Noida query. One email each with NAP + portfolio + 3 frames.
2 Wedding platforms | — | WedAbout | — | — | — | — | — | SKIP | Cert expired, unfunded since 2015.
3 B2B / creative | W3 | Clutch | https://clutch.co/get-listed | Free basic (Verified $499/yr — decline) | Company email/LinkedIn; team review | Website URL shown (nofollow) | Video Production -> Corporate Video; Post Production | P0 | clutch.co/in/agencies/video-production/delhi shows for both Delhi video queries. Ask 2 corporate clients for Clutch reviews (phone interview or form).
3 B2B / creative | W3 | GoodFirms | https://www.goodfirms.co/get-listed | Free | 5-10 business days; categories cannot be edited later | nofollow on free | Video Production | P1 | Choose categories carefully first time.
3 B2B / creative | W3 | DesignRush | https://www.designrush.com/submit/agency | Free basic | Portfolio/website review | Website link | Video Production | P1 | designrush.com/agency/video-production/in/delhi ranks.
3 B2B / creative | W3 | TechBehemoths | https://techbehemoths.com | Free | Email | Website link | Video Production | P1 | Has Noida + Gurgaon video-production pages.
3 B2B / creative | W4 | Sortlist | https://www.sortlist.com | Listing free (unverified); leads ~$500 — never buy | — | Profile | Video | P2 | sortlist.com/video/noida-up-in ranks.
3 B2B / creative | W4 | ProductionHUB | https://www.productionhub.com/get-listed | Free basic (1 video + 1 gallery) | Email | Website on paid only | Video Production Company | P2 | Not seen in Delhi SERPs; low priority citation.
3 B2B / creative | W1 | Behance (fill the empty profile) | https://www.behance.net/thelastclicks | Free | — | Profile link | 6 projects, one per vertical | P1 | Currently 'This team has no projects' while linked sitewide. Buyer-language titles.
3 B2B / creative | W1 | Vimeo profile + showcase | https://vimeo.com | Free | — | Profile link | Showcase per vertical | P1 | Second video host; curators scout Vimeo. NAP in bio.
3 B2B / creative | W1 | LinkedIn company page — complete | https://www.linkedin.com/company/thelastclicks | Free | — | Website (nofollow) | Media Production | P1 | LinkedIn cited in 14.3% of ChatGPT answers (Semrush). Add address, hours, specialties, 4 posts/month.
3 B2B / creative | W1 | Facebook page — confirm URL, add to footer sameAs | facebook.com | Free | — | Website | Photographer / Video production | P1 | Facebook = 10.1% of AIO citations (Ahrefs Sep 2026). NAP exact, hours, 'Services' tab.
3 B2B / creative | W4 | Love Stories TV (wedding films) | https://lovestoriestv.com/for-filmmakers | Free | — | Business page = citation | Wedding filmmaker | P2 | Upload 5 wedding films -> business page; awards eligibility at 5+.
3 B2B / creative | — | Crunchbase · Wikidata · Production Paradise · Mandy | — | — | — | — | — | SKIP | Crunchbase removes non-tech; Wikidata forbids self-created items; Production Paradise $2-5k; Mandy paid. Revisit month 3+.
4 Local / institutional | W2 | Udyam (MSME) registration | https://www.udyamregistration.gov.in | Free | Aadhaar/PAN | None public | — | P1 | Not a crawlable citation but unlocks IndiaMART/Justdial verified badges. 30 min.
4 Local / institutional | — | CII membership | https://www.cii.in | ₹3,300 entry + ₹7,700-23,200/yr + GST | Audited accounts | Member directory (unverified) | — | P3 | Month 3 decision. PHDCCI needs ₹1 Cr turnover — skip. FICCI — skip.
4 Local / institutional | — | Startup India (DPIIT) | https://www.startupindia.gov.in | Free | Incorporation docs | Public dataset | — | P3 | Only if entity is Pvt Ltd/LLP/partnership.

## 05 Citations · NAP master
Copy-paste from here only. Byte-identical on every platform.
Field | Value
name | TheLastClicks
name_rule | Drop '(TLC)' from GBP — Google name policy forbids parenthetical add-ons; 'TLC' goes in description only
address | B-7, D-Block, Sector 26, Noida, Uttar Pradesh 201301
country | India
phone_display | +91 87701 55842
phone_e164 | +918770155842
email | info@thelastclicks.com
website | https://thelastclicks.com
hours | Mon-Sat 10:00-19:00
gbp_primary | Video production service
gbp_secondary | Photography studio; Photographer; Commercial photographer; Film production company; Video editing service; Wedding photographer (confirm in GBP UI); Media company
description_120 | Photography, video production and in-house post-production studio in Sector 26, Noida. Corporate event films and aftermovies, brand films, wedding and pre-wedding films, live-music films, podcast video, property walkthroughs — across Delhi NCR and India.
lat | 28.5808331
lng | 77.3328251

## 05 Citations · rules
# | Rule
1 | One NAP string everywhere, byte-identical: name / B-7, D-Block, Sector 26, Noida, Uttar Pradesh 201301 / +91 87701 55842. E.164 (+918770155842) only inside tel: links and schema.
2 | Decide the canonical name on W1 D1 and never revisit: GBP must drop '(TLC)' (Google name policy). Website Brand::NAME, footer, schema and every directory must match it.
3 | Same description paragraph (120 words) and same logo file on every profile. Same 6 buyer-language service labels: Corporate event video & aftermovies · Brand films · Wedding & pre-wedding films and photos · Live concert films · Podcast video · Property walkthroughs. Plus 'Video editing & colour grading'.
4 | Never buy: Justdial priority, Sulekha leads, IndiaMART TrustSEAL, WedMeGood Premium, Clutch Verified, Sortlist leads, listicle 'featured' slots. Free tier only this month; revisit with month-two data.
5 | No ₹ figures on any profile ('price on request'). No turnaround claims.
6 | Log every listing in the Citations tab with the live URL the day it goes live. Then add the URL to the site's Organization sameAs (one PR, week 4).
7 | Keep login/OTP details in the password manager under 'citations/<platform>' — abandoned listings become unfixable duplicates (#2 negative local factor).
8 | Reviews on third-party platforms count as AI factor #5: after the listing is live, route one client each to WeddingWire, WedMeGood, Clutch.

## 05 Roundups & pitches
Week | Target | URL | Type | Route | Ask / outcome wanted | Why | Pitched on | Reply? | Result URL
W3 | Clutch Delhi video production list | https://clutch.co/in/agencies/video-production/delhi | Directory ranking (review-driven) | Free profile + 2 client reviews | Profile live + 2 verified reviews | Appears in both 'video production Delhi' queries; review count drives rank
W3 | DesignRush Delhi video production | https://www.designrush.com/agency/video-production/in/delhi | Directory | Free submit | Listing approved | Ranks for Delhi query
W3 | GoodFirms Delhi video production | https://www.goodfirms.co/directory/city/top-digital-marketing-companies/video-production/delhi | Directory | Free submit (5-10 days) | Listing approved | Ranks for Delhi query
W3 | TechBehemoths Noida video production | https://techbehemoths.com/companies/video-production/noida | Directory | Free | Listing live | Only list with a Noida-specific page
W4 | Vidsaga 'Top video production companies in Delhi' | https://www.vidsaga.com/top-video-production-companies-in-delhi-2/ | Marketplace blog | Email via site + 'Submit Video Requirement' | Inclusion in next refresh; one quotable detail (44 finished films, six verticals, in-house DaVinci grade) | Recurs across Delhi SERPs; editorial
W4 | Sloshout '10 most popular wedding photographers Delhi NCR' | https://www.sloshout.com/blog/10-most-popular-wedding-photographers-in-delhi-ncr-for-couples/ | Marketplace blog (7 Oct 2025) | info@sloshout.com | Inclusion in 2026 refresh + vendor listing | Ranks; editorial; annual refresh due Oct
W4 | Entrepreneur Hunt 'Top 10 podcast studios Delhi NCR 2026' | https://www.entrepreneurhunt.com/top-10-podcast-content-creation-studios-in-delhi-ncr-to-watch-in-2026 | News-style site (5 Feb 2026) | Site contact page | Inclusion (likely asks for payment — decline paid; accept editorial) | Only podcast listicle found
W4 | WedMeGood Real Weddings | https://www.wedmegood.com/submit-real-wedding | Real-wedding feature | submissions@wedmegood.com; 15-20 photos + story | Feature with vendor credit | Most-cited wedding domain; free
W4 | WeddingSutra real wedding | https://weddingsutra.com/submit-a-wedding/ | Real-wedding feature | editor@weddingsutra.com; 8-10 photos across functions; unpublished; 90-day exclusivity | Feature with photographer credit | Editorial credit; choose a wedding NOT sent to WMG (exclusivity)
Month 2 | Junebug Weddings vendor application | https://junebugweddings.com/photographer-application | Vendor directory (needs 2 yrs, 30+ weddings) | Application; decision ~10 days | Membership | Links photographer site; price unpublished
Month 2 | Directors Notes (brand/liquor film) | https://directorsnotes.com/submit/ | Curated film blog | £47 submission | Feature | Only realistic paid curation for a brand film; Vimeo Staff Picks scouts it
SKIP | Agency-blog 'Top 5 in Noida/Delhi' lists (indievisual, ritzmediaworld, shunyanant, 3dtrixs, knotsbyamp, wedpicstudio) | — | Competitor self-promo | None | — | Closed lists; no route in. Don't waste pitches.

## 06 Baseline · prompts
ID | Bucket | Prompt
B1 | Brand | TheLastClicks Noida photography and video studio — what do they do?
B2 | Brand | Is The Last Clicks (TLC) in Noida a good video production studio?
L1 | Local-commercial | best wedding photographers in Noida
L2 | Local-commercial | best corporate video production companies in Delhi NCR
L3 | Local-commercial | corporate event videographer in Noida
L4 | Local-commercial | pre-wedding photographer in Noida
L5 | Local-commercial | podcast video production studio in Noida or Delhi
L6 | Local-commercial | video editing and colour grading studio in Delhi NCR
I1 | Informational | what does video post-production include
I2 | Informational | what is an aftermovie
I3 | Informational | how to choose a corporate video production company in India
I4 | Informational | what drives the cost of video editing in India
I5 | Informational | best pre-wedding shoot locations in Delhi NCR
I6 | Informational | how to brief a video production team

## 06 Baseline · engines
Engine | Clean-test method | Cost
Google AI Overview | Incognito Chrome, google.co.in, Search settings location = Noida. Log whether an AIO appears at all. | Free
Google AI Mode | Incognito, google.co.in/aimode. India has AI Mode since 8 Jul 2025. | Free
ChatGPT (search on) | Temporary Chat (memory off), force 'Search the web'. Log all cited sources (ChatGPT cites ~15 per answer). | Free tier OK
Perplexity | Set profile location to Noida; new thread each prompt; note model (free vs Pro). | Free
Gemini | New chat, Personal Intelligence off. Gemini names brands 83.7% but links only 21.4% — log 'mentioned' separately. | Free
Microsoft Copilot | Signed-out, region India. Cross-check with Bing Webmaster Tools AI Performance report. | Free

## 06 Baseline · AI log
84 pre-filled rows = 14 prompts × 6 engines for the W1 baseline. Duplicate the block for the W4 re-measure. Mentioned ≠ cited: log both.
date | run (W1 baseline / W4 remeasure) | engine | prompt_id | prompt | ai_answer_shown? (Y/N) | brand_status (cited / mentioned / absent) | position_in_answer | our_url_cited | competing_domains_cited (comma) | verbatim_snippet (first 200 chars) | screenshot_file | notes
|  | Google AI Overview | B1 | TheLastClicks Noida photography and video studio — what do they do?
|  | Google AI Overview | B2 | Is The Last Clicks (TLC) in Noida a good video production studio?
|  | Google AI Overview | L1 | best wedding photographers in Noida
|  | Google AI Overview | L2 | best corporate video production companies in Delhi NCR
|  | Google AI Overview | L3 | corporate event videographer in Noida
|  | Google AI Overview | L4 | pre-wedding photographer in Noida
|  | Google AI Overview | L5 | podcast video production studio in Noida or Delhi
|  | Google AI Overview | L6 | video editing and colour grading studio in Delhi NCR
|  | Google AI Overview | I1 | what does video post-production include
|  | Google AI Overview | I2 | what is an aftermovie
|  | Google AI Overview | I3 | how to choose a corporate video production company in India
|  | Google AI Overview | I4 | what drives the cost of video editing in India
|  | Google AI Overview | I5 | best pre-wedding shoot locations in Delhi NCR
|  | Google AI Overview | I6 | how to brief a video production team
|  | Google AI Mode | B1 | TheLastClicks Noida photography and video studio — what do they do?
|  | Google AI Mode | B2 | Is The Last Clicks (TLC) in Noida a good video production studio?
|  | Google AI Mode | L1 | best wedding photographers in Noida
|  | Google AI Mode | L2 | best corporate video production companies in Delhi NCR
|  | Google AI Mode | L3 | corporate event videographer in Noida
|  | Google AI Mode | L4 | pre-wedding photographer in Noida
|  | Google AI Mode | L5 | podcast video production studio in Noida or Delhi
|  | Google AI Mode | L6 | video editing and colour grading studio in Delhi NCR
|  | Google AI Mode | I1 | what does video post-production include
|  | Google AI Mode | I2 | what is an aftermovie
|  | Google AI Mode | I3 | how to choose a corporate video production company in India
|  | Google AI Mode | I4 | what drives the cost of video editing in India
|  | Google AI Mode | I5 | best pre-wedding shoot locations in Delhi NCR
|  | Google AI Mode | I6 | how to brief a video production team
|  | ChatGPT (search on) | B1 | TheLastClicks Noida photography and video studio — what do they do?
|  | ChatGPT (search on) | B2 | Is The Last Clicks (TLC) in Noida a good video production studio?
|  | ChatGPT (search on) | L1 | best wedding photographers in Noida
|  | ChatGPT (search on) | L2 | best corporate video production companies in Delhi NCR
|  | ChatGPT (search on) | L3 | corporate event videographer in Noida
|  | ChatGPT (search on) | L4 | pre-wedding photographer in Noida
|  | ChatGPT (search on) | L5 | podcast video production studio in Noida or Delhi
|  | ChatGPT (search on) | L6 | video editing and colour grading studio in Delhi NCR
|  | ChatGPT (search on) | I1 | what does video post-production include
|  | ChatGPT (search on) | I2 | what is an aftermovie
|  | ChatGPT (search on) | I3 | how to choose a corporate video production company in India
|  | ChatGPT (search on) | I4 | what drives the cost of video editing in India
|  | ChatGPT (search on) | I5 | best pre-wedding shoot locations in Delhi NCR
|  | ChatGPT (search on) | I6 | how to brief a video production team
|  | Perplexity | B1 | TheLastClicks Noida photography and video studio — what do they do?
|  | Perplexity | B2 | Is The Last Clicks (TLC) in Noida a good video production studio?
|  | Perplexity | L1 | best wedding photographers in Noida
|  | Perplexity | L2 | best corporate video production companies in Delhi NCR
|  | Perplexity | L3 | corporate event videographer in Noida
|  | Perplexity | L4 | pre-wedding photographer in Noida
|  | Perplexity | L5 | podcast video production studio in Noida or Delhi
|  | Perplexity | L6 | video editing and colour grading studio in Delhi NCR
|  | Perplexity | I1 | what does video post-production include
|  | Perplexity | I2 | what is an aftermovie
|  | Perplexity | I3 | how to choose a corporate video production company in India
|  | Perplexity | I4 | what drives the cost of video editing in India
|  | Perplexity | I5 | best pre-wedding shoot locations in Delhi NCR
|  | Perplexity | I6 | how to brief a video production team
|  | Gemini | B1 | TheLastClicks Noida photography and video studio — what do they do?
|  | Gemini | B2 | Is The Last Clicks (TLC) in Noida a good video production studio?
|  | Gemini | L1 | best wedding photographers in Noida
|  | Gemini | L2 | best corporate video production companies in Delhi NCR
|  | Gemini | L3 | corporate event videographer in Noida
|  | Gemini | L4 | pre-wedding photographer in Noida
|  | Gemini | L5 | podcast video production studio in Noida or Delhi
|  | Gemini | L6 | video editing and colour grading studio in Delhi NCR
|  | Gemini | I1 | what does video post-production include
|  | Gemini | I2 | what is an aftermovie
|  | Gemini | I3 | how to choose a corporate video production company in India
|  | Gemini | I4 | what drives the cost of video editing in India
|  | Gemini | I5 | best pre-wedding shoot locations in Delhi NCR
|  | Gemini | I6 | how to brief a video production team
|  | Microsoft Copilot | B1 | TheLastClicks Noida photography and video studio — what do they do?
|  | Microsoft Copilot | B2 | Is The Last Clicks (TLC) in Noida a good video production studio?
|  | Microsoft Copilot | L1 | best wedding photographers in Noida
|  | Microsoft Copilot | L2 | best corporate video production companies in Delhi NCR
|  | Microsoft Copilot | L3 | corporate event videographer in Noida
|  | Microsoft Copilot | L4 | pre-wedding photographer in Noida
|  | Microsoft Copilot | L5 | podcast video production studio in Noida or Delhi
|  | Microsoft Copilot | L6 | video editing and colour grading studio in Delhi NCR
|  | Microsoft Copilot | I1 | what does video post-production include
|  | Microsoft Copilot | I2 | what is an aftermovie
|  | Microsoft Copilot | I3 | how to choose a corporate video production company in India
|  | Microsoft Copilot | I4 | what drives the cost of video editing in India
|  | Microsoft Copilot | I5 | best pre-wedding shoot locations in Delhi NCR
|  | Microsoft Copilot | I6 | how to brief a video production team

## 06 Baseline · weekly
week_start | GSC brand impressions (regex) | GSC brand clicks | GSC non-brand impressions | GSC non-brand clicks | GSC 'Generative AI' impressions | GSC pos: 'video post production' | Bing WMT AI citations | Bing WMT cited pages | GBP profile views | GBP calls | GBP direction requests | GBP website clicks | GBP top search terms (top 3) | Google reviews (count / rating) | Live directory listings (count) | Reddit karma (post / comment) | Quora answer views (total) | Roundup placements (pitched / live) | notes
2026-09-08
2026-09-15
2026-09-22
2026-09-29
2026-10-06 (month-end)

## 06 Baseline · setup steps
When | Step | Est. hrs | Done?
W1 D1 | GSC: Performance > Search results > Query filter 'Custom (regex)' = (?i)(the\s?)?last\s?clicks¦thelastclicks¦tlc\s?(noida¦studio). Export last 28 days AND last 3 months. Record brand vs non-brand impressions/clicks. Note Aug baseline 65 + 108. | 0.25
W1 D1 | GSC: open the 'Generative AI performance' report (worldwide since 31 Aug 2026; impressions only, AIO + AI Mode combined). Record the 28-day number even if 0. | 0.1
W1 D1 | GSC: Performance > filter query contains 'post production' — log position for 'video post production' (was 57-64). | 0.1
W1 D1 | Bing Webmaster Tools: verify site (import from GSC), enable IndexNow, open 'AI Performance' report; record citations/cited pages (likely 0). | 0.3
W1 D1 | GBP Performance (last 28 days): views (Search/Maps), calls, directions, website clicks, top search terms. Screenshot. | 0.15
W1 D2 | Run the 14 prompts on 6 engines = 84 runs. Log each row in 'Baseline · AI log'. Screenshot every answer that names any Noida/Delhi studio — those are the competitors AI already trusts. | 1.5
W1 D2 | From the AI log, list every third-party domain cited for the L-bucket prompts (WedMeGood, Clutch, DesignRush, Justdial, Reddit thread, Quora question…). That list becomes the priority order for the Citations tab. | 0.25
W4 D26 | Repeat the 84 runs (same hygiene). Compare: cited/mentioned counts, which competitor domains dropped or appeared, whether any of our 4 posts got cited for I-bucket prompts. | 1.5
W4 D27 | Pull GSC (brand regex + Generative AI report), Bing AI Performance, GBP Performance. Fill the W4 row. Write 10-line month-two brief from the deltas. | 0.5